## Sheet1
Activity type | Activity | Completed
On-boarding and commercials | Requested access to Street Manager Sandbox and Production
On-boarding and commercials | Received, completed/signed and returned requested information and T&Cs
On-boarding and commercials | Read additional documentation such as security information
On-boarding and commercials | Activated access to Sandbox and Production
Sandbox testing - UI | Set up users in Sandbox
Sandbox testing - UI | Performed end to end testing in Sandbox
Business change | Performed gap analysis
Business change | Performed impact assessment
Business change | Validated transition decision (eg. UI vs API vs both)
Business change | Developed a transition plan
Business change | Developed a stakeholder engagement plan
Business change | Identified user training needs
Business change | Delivered user training successfully
Business change | Engaged with all contractors and relevant 3rd parties
Business change | Agreed with contractors how they can be set up in Street Manager
Business change | Confirmed with contractors that they have been set up in Street Manager
Transition to Production via UI - if using the UI | Primary contact authorises move to production via UI
Transition to Production via UI - if using the UI | Primary contact communicates decision to DfT
Transition to Production via UI - if using the UI | Set up users in Production
Transition to Production via UI - if using the UI | Set up workstreams
Transition to Production via UI - if using the UI | Associate any contractors to workstreams if applicable
Transition to Production via UI - if using the UI | Primary contact communicates decision to other organisations as applicable
Transition to Production via UI - if using the UI | Move to production via UI
Transition to Production via UI - if using the UI | Post-launch quality assurance of data in production
Sandbox dev & testing - API - if using API | Developed API (in-house or externally) based on API spec provided by DfT
Sandbox dev & testing - API - if using API | Tested API in sandbox environment- if applicable
Transition to Production via API - if using API | Primary contact authorises move to production via API
Transition to Production via API - if using API | Primary contact communicates decision to DfT
Transition to Production via API - if using API | Primary contact communicates decision to other organisations as applicable
Transition to Production via API - if using API | Move to production via API and set up users and workstreams
Transition to Production via API - if using API | Post-launch quality assurance of data in production
Transition to Production via API - if using API | Post-launch API updates as and when needed with test in Sandbox environment first