## 1. Project summary
Project Name: | DfT Street Manager
Content links | 2. Guidance and best practice
3. Tool navigation
4. Impact assessment tool
5. Visualisation
6. Pivot tables

## 2. Guidance and best practice
Why should I do a Change Impact Assessment
A Change Impact Assessment allows you to understand how moving to Street Manager wil impact your organisation holistically - this means not only assessing in detail how it will impact organisational elements in isolation (people, processes, technology, ways of working), but also understanding the wider picture and all dependencies and links between these elements. This is critical to enable you to plan how and when to deliver the change, define KPIs and desired outcomes and allocate resources.
When should I do a Change Impact Assessment
An Impact Assessment is usually performed at the beginning of any project to aid planning, however it is a good practice to treat this as a live document and monitor any movements so that the plan can be kept relevant and updated if needed. It is also advisable to repeat the overall assessment at a later stage to ensure that it takes into account any updates in available information, e.g.: You might not be clear whether to go API vs UI route because you need more technical information. A month down the line more information becomes available. Doing Impact assessment for your preferred (or both) scenarios now that you have more information will enable you to firm your project plan and make any necessary changes.
Questions to consider when doing a Change Impact Assessment
Organisation area | Questions to consider | Possible implications and considerations
People - population size | How many people are currently working on permit/noticing systems? | Current population affected - implications for communications, awareness and expectations management
People - population size | How many people will be using Street Manager? | Stakeholder engagement and buy-in
People - population size | If number is different, what is the reason for this? | Possible need for consultation (if FTE is being reduced) or recruitment (if FTE is being increased) or relocation of workforce within the organisaiton.
People - roles and responsibilities | Would there be any change of roles and responsibilities? | Possible need for negotiation of contracts and job descriptions and upskilling
People - organisation structure | Would there be any change in organisation structures? | Organisation re-design, redeployment of staff and possible consultation
People - organisation structure | Would there be any change in reporting lines? | Communications and possible contract re-negotiation
People - culture and behaviour | Would there be a need for shift in culture or ways of working? | Communications and possible contract re-negotiation (e.g. if ways of working are changing)
Processes - number of processes affected | How many business processes will be affected by the change? | Link to related business outcomes and teams involved in delivery: What measures do we need to have in place and who needs to be involved to ensure successful delivery?
Processes - number of processes affected | Would there be any new processes required to deliver outcomes? | Link to roles and responsibilities, staff capacity and user journey: How do we make sure that user journey is not impacted negatively?
Processes - number of processes affected | Would any of the existing processes cease to exist? | Link to roles and responsibilities, staff capacity and user journey: How do we minimse disruption to BAU?
Processes - complexity of processes | How complex are the impacted processes? | Time required to transition, business change required to support to-be process adoption, risks of BAU disruption
Processes - complexity of processes | How many handoffs and interdependencies exist between affected processes? | Approach to transitioning to new processes (e.g. big bang or phased), risks of BAU disruption
Processes - complexity of processes | What other dependencies and linkages to other processes do need to be considered? | Approach to transitioning to new processes (e.g. big bang or phased), risks of BAU disruption
Technology - adoption approach | Is API the preferred adoption method to use Street Manager? | Lead time and investment required to develop API, lower level of change in user experience, no need for extensive system training
Technology - adoption approach | Is UI/Web app the preferred adoption method to use Street Manager? | Higher level of change in user experience and requirement for training on new UI
Technology - IT environment | How complex is the current IT environment when it comes to permit/noticing systems? | Gap analysis and transition planning to assess what can be replaced when, review of contractual agreements with software vendors
Technology - IT environment | Are current permit/noticing systems integrated to other software - e.g. asset management? | Engagement and collaboration with service providers of those systems, planning for and delivery of system integration work (e.g. via API)
Technology - IT environment | How many external IT systems (other LHAs/Utilities/contractors) would SM need to interact with? | Implications for length of duration of dual-running period, joint planning for transition
Technology - IT environment | Would there be a need for dual-running with current permit/noticing systems even after all linked external organisations have transitioned to Street Manager? | Resource requirements, review of workflows and quality assurance to minimise risk of any work falling through the gaps
Technology - IT capability | Is software mainly been developed and serviced internally or outsourced? | Time and capability required to build API / deliver system integration
Technology - IT capability | What are the organisation's relations with software vendors? | Level of flexibility to renegotiate contracts, source new vendors, cost of IT
Links and dependencies | What is the priority organisational element that will be considered when it comes to designing the desired future state? | Benefits and KPIs definition, acceptable trade-offs between benefits and investment required to achieve them
Links and dependencies | How does this align to organisaitonal strategy? | Benefits and KPIs definition, acceptable trade-offs between benefits and investment required to achieve them
Note:
When assessing impact on processes, you might find it useful to refer to the Street Manager business rules and workflows documented here:
https://departmentfortransport.github.io/street-manager-docs/business-rules/#business-rules
Please, note that the documentation of business rules is work in progress and is being updated as and when required, and it is possible that they will change as the system develops.
The business rules documentation is being trialled for use with the Street Manager private beta only, it is not in final state and should not be taken as production documentation.
UPDATED

## 3. Tool navigation
Tool usage guidance and assessment principles (refer to best practice questions when completing)
Field | Sub-field | Information to fill | Comments
Type of impact: primary | Organisation element | Pre-populated for People | Note this row assesses the impact from the perspective of People - it takes into account linkages to other elements, but the centre is on People
Type of impact: primary | Organisation element | Pre-populated for Process | Note this row assesses the impact from the perspective of Processes - it takes into account linkages to other elements, but the centre is on Processes
Type of impact: primary | Organisation element | Pre-populated for Technology | Note this row assesses the impact from the perspective of Technology - it takes into account linkages to other elements, but the centre is on Technology
Type of impact: primary | Organisation element | Pre-populated for Ways of working | Note this row assesses the impact from the perspective of Ways of working - it takes into account linkages to other elements, but the centre is on Ways of working
Type of impact: primary | Organisation element | If any other - Select 'Other' | Which is the main organisation element that you want to assess the impact on?
Type of impact: primary | Name / description of element | For people: Name of department / team / individual / roles impacted; For processes: Name / description of process For technology: Name of system For ways of working: Description For other: Description | Note that for each element you will need separate rows to assess the impact on more than one entry (e.g. two processes will require two separate assessments)
Current state | Current state summary | Describe the current state / method / activity in terms of Process, People and Technology involved in managing information on street and roadworks. | e.g. 10 people currently managing permits on EToN system
Future state | Future state summary | Describe the future state / method / activity in terms of Process, People and Technology involved in managing information on street and roadworks. | e.g. 12 People working on Street Manager Webapp for permits on emergency works, non-emergency works remaining on EToN and linking to Street Manager via API
Gap | Gap summary | Describe how different the future state will be from the current state | New system to be introduced plus development of API. Change in processes and upskilling required
Level of impact: primary | Level of impact: primary | High / Medium / Low / Not known | When possible determine the level even if not 100% certain
Level of impact: secondary | Number of people affected | Number
Level of impact: secondary | Level of impact on people | H / M / L | Consider dependency on people - how would they be impacted
Level of impact: secondary | Number of processes affected | Number
Level of impact: secondary | Level of impact on processes | H / M / L | Consider dependency on processes - how would they be impacted
Level of impact: secondary | Number of systems affected | Number
Level of impact: secondary | Level of impact on technology | H / M / L | Consider dependency on systems - how would they be impacted
Priority* | Overall priority based on primary and secondary impact | Auto populated via formula** | Assumptions: - High Primary, and High on all secondary elements = Very High - High Primary, and a mixture of H/M/L on secondary elements = High - Medium Primary, and High on all secondary elements = High - Low Primary, and Low on all secondary elements = Low - all other scenarios = Medium
SWOT | Underlying strenghts to support change | Describe factual strenghts that can be draw on | E.g. ultimately Street Manager will minimise manual hand-offs
SWOT | Opportunities | Describe opportunities to aid managing change based on the listed strenghts
SWOT | Underlying weak points to be taken into account | Describe factual weak points that need to be considered | E.g. a period of dual running will increase requirements for resource
SWOT | Risks | Describe risks to delivering successfully change
SWOT | Mitigation | Describe mitigation methods to minimise negative impact | Consider link to Opportunities
Other comments | Other comments | Other comments
* *Yellow cells contain formulas
*Priority is for supporting guidance only - you do not need to necessarily abide by this when planning and delivering the change

## 4. Impact assessment tool
Type of impact: primary |  | Current state summary | Future state summary | Gap | Level of impact: primary | Level of impact: secondary | [5 empty] | Priority | Strengths, weaknesses, opportunities and risks |  |  |  |  | Other comments
Main organisational element that will be impacted (select: People, Process, Technology, Ways of working, Other) | Organisational element name (e.g. name of IT system / stakeholder / team / department that is being impacted by the move to Street Manager) | Describe the current state / method / activity in terms of Process, People and Technology involved in managing information on street and roadworks. (e.g. 10 people currently managing permits on EToN system) | Describe how the end state will look like e.g. 12 People working on Street Manager Website for permits on emergency works, non-emergency works remaining on EToN and linking to Street Manager via API | Describe how different is the future state from the current state | High / Medium / Low / Not known | Number of People affected | Impact on People (H/M/L) | Number of Processes affected | Impact on Processes (H/M/L) | Number of systems affected | Impact on Tech (H/M/L) | Overall priority based on primary impact and secondary impact (AUTO FORMULA) | Underlying strengths / advantages that can be used to support change | Underlying weak points that need to be considered when delivering change | Related key risks | Mitigation | Opportunities | (e.g. narative description of the change and context relating to the stakeholders group)
People |  |  |  |  | High |  | H |  | H |  | H | Very High
Process |  |  |  |  | High |  | M |  | H |  | M | High
Technology |  |  |  |  | Medium |  | H |  | H |  | H | High
Ways of Working |  |  |  |  | Medium |  | H |  | M |  | M | Medium
People |  |  |  |  | Low |  | L |  | L |  | L | Low
Select |  |  |  |  | Low |  | H |  | M |  | L | Medium
Process |  |  |  |  | Not known |  | H |  |  |  |  | Medium
Other | [6 empty] | H |  |  |  |  | Medium
Select | [6 empty] | H |  |  |  |  | Medium
Select | [6 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | M |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | L |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium |  |  | Very opposed to change
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | M |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | M |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | M |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | M |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium |  |  | Resistent to change and unhappy with professionalism of current approach
[7 empty] | H |  |  |  |  | Medium
[7 empty] | M |  |  |  |  | Medium
[7 empty] | M |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | M |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | M |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | M |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium |  |  | Negative sentiments towards the way that the project has been delivered
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | L |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
[7 empty] | H |  |  |  |  | Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium
Medium

## 6. Pivots
Overall priority | Overall priority based on primary impact and secondary impact
Main org element | High | Low | Medium | Very High
Other |  |  | 1
People |  | 1 |  | 1
Process | 1 |  | 1
Technology | 1
Ways of Working |  |  | 1
Grand Total | 2 | 1 | 3 | 1
Overall priority based on primary impact and secondary impact (AUTO FORMULA) | Very High
Very high priority | Primary impact on main element
Main org element | High
People | 1
Grand Total | 1
Overall priority based on primary impact and secondary impact (AUTO FORMULA) | High
High priority | Primary impact on main element
Main org element | High | Medium
Process | 1
Technology |  | 1
Grand Total | 1 | 1