## 1. Project summary
Project Name: | DfT Street Manager
Content links | 2. Guidance and best practice
3. Stakeholder analysis and engagement
4. Pivots
5. Visualisation Dashboard

## 2. Guidance and best practice
Why should I do a Stakeholder Analysis
A stakeholder analysis will allow you to break down the different groups within your organsiation and understand where they stand in terms of support for the change as well as the level of influence they may exert. This will allow you to understand who will be a champion of the change, voicing their support for the change throughout the organisation and those who will be blockers, actively challenging the change. As a result, you will be able to use the stakeholder analysis to form the basis of your engagment and communications approach.
When should I do a Stakeholder Analysis
A Stakeholder Analysis is usually performed at the beginning of any project to aid planning, however it is a good practice to treat this as a live document and monitor any movements so that the plan can be kept relevant and updated if needed. It is also advisable to repeat the overall assessment at a later stage to ensure that it takes into account any updates in available information, e.g.: move those over who have now come on board away with the change
How do I do a Stakeholder Analysis
1) You should break your stakeholders down into individuals if size allows but you can also group people if needed. 2) You should consider the impact of the change on the individual as well as their influence within your organisation - if you have completed the Impact assessment and the Readiness assessment and have included these stakeholders you can take the H/M/L values from there. 3) The individual's sentiment towards the change should be considered - they will either be supportive (S), neutral (N) or resistant (R). 4) The sheet is set up with an automatic formula that matches an individual's level of influence with their sentiment to allocate them one of the below categories: -Champion: High Influence and Supporter -Adopter: Low Influence and Supporter -Observer: High or Low Influence and Neutral -Opposer: Low Influence and Resistant -Blocker: High Influence and Resistant 5)The tool also highlights where engagement is needed (e.g. for Champions and Blockers) and allows you to plan engagement - e.g. :you can decide if they answer is they do or do not need a particular type of engagement or training such as via online business channels or face 2 face engagement. 6)There is an example provided for you, which you should overwrite with your content.
Questions to consider when doing a Stakeholder Analysis
Organisation area | Questions to consider | Possible implications and considerations
People - population size | How many people are currently working on permit/noticing systems? | The number will help you work out who needs to be included in the stakeholder analysis
People - population size | How many people will be using Street Manager? | The number will help you work out who needs to be included in the stakeholder analysis
People - roles and responsibilities | Would there be any change of roles and responsibilities? | This will dictate the impact of the change on the individual
People - organisation structure | Would there be any change in organisation structures? | This will dictate the impact of the change on the individual
People - organisation structure | Would there be any change in reporting lines? | This will dictate the impact of the change on the individual
People - culture and behaviour | Would there be a need for shift in culture or ways of working? | This will dictate the impact of the change on the individual
Processes - number of processes affected | How many business processes will be affected by the change? | This will dictate the impact of the change on the individual
Processes - number of processes affected | Would there be any new processes required to deliver outcomes? | This will dictate the impact of the change on the individual
Processes - number of processes affected | Would any of the existing processes cease to exist? | This will dictate the impact of the change on the individual
Processes - complexity of processes | How complex are the impacted processes? | This will dictate the impact of the change on the individual
People - Engagement | Have people been engaged? | This will impact the sentiment as well as your ability to determine their sentiment.
People - Engagement | Do they understand their future role? | This will impact the sentiment as well as your ability to determine their sentiment.
People - Engagement | Do they need to be trained? | This will dictate the impact of the change on the individual
People - Engagement | Have they already been trained? | This will dictate the impact of the change on the individual
People - Engagement | Do they feel confident to settle into the future state? | This will dictate the impact of the change on the individual
Processes - Future | Do you know the dependencies? | This will dictate the impact of the change on the individual
Processes - Future | Do you have a mitigation plan for any disruptions? | This will dictate the impact of the change on the individual

## 3. Stakeholder analysis and en
Stakeholder Details |  |  | Impact of change on stakeholder | Influence of stakeholder on others | Sentiment towards the move to SM | Readiness to transition | Stakeholder grouping | Engagement so far | Engagement needed as a priority | Which of the following engagement interventions need to be implemented to support this stakeholder group? Yes = Must be put in place No = Doesn't need to be put in place Maybe = Could be put in place if time / resource permits | [5 empty] | Which of the following training interventions need to be implemented to support this stakeholder group? |  |  |  | Comment
Name | Department | Role | H/M/L | H/L | S/N/R | H/M/L | Champion / Adopter/ Observer / Opposer / Blocker | Yes / No | Yes for Champtions and Blockers | 1-2-1 targeted engagement | Engagement from Leadership | Engagement via f2f | Engagement via online business channels (e.g. email / social channel) | Newsletter | Involvement in community / support network | Video tutorials / demos | Online FAQ / Q&A platform | Reference guide | F2f / web conference training
Name | Department | Role | H/M/L | H/L | S/N/R | H/M/L | Observer
e.g. John Smith 1 | Gas | Traffic manager | H | H | S | M | Champion | Yes | Yes | Yes | Yes | Yes | Yes | Maybe | Yes | Yes | Yes | Maybe | Maybe
e.g. John Smith 2 | Water |  | H | H | R | L | Blocker |  | Yes
e.g. John Smith 3 | Gas |  | M | H | N | M | Observer
e.g. John Smith 4 | Water |  | H | L | S | H | Adopter
e.g. John Smith 5 | Gas |  | M | L | R | L | Opposer
e.g. John Smith 6 | Gas |  | L | L | N | M | Observer
Observer
Observer
Observer
Observer
Observer
Observer
Observer
Observer
Observer
Observer
Observer
Observer
Observer
Observer
Observer
Observer
Observer
Observer
Observer
Observer
Observer
Observer
Observer
Observer
Observer
Observer
Observer
Observer
Observer
Observer
Observer
Observer
Observer
Observer
Observer
Observer
Observer
Observer
Observer
Observer
Observer